## Man-Hours Estimate
Pre-LLM Development Estimate: Space Visualization Project
Estimated man-hours for a senior Three.js / WebGL developer (solo) — traditional development without AI assistance
Component | Low (hrs) | High (hrs) | Mid (hrs) | Notes
SOLAR SYSTEM MAP |  |  |  | ~2,700 lines • Single-file HTML/JS/CSS
Orbital mechanics (Kepler solver) | 40 | 60 | 50 | Mean/eccentric anomaly, elliptical orbits, inclination, argument of perihelion
Asinh distance compression | 12 | 20 | 16 | Custom non-linear scale with smooth near-origin behavior; lots of tuning
Procedural planet textures (×10 types) | 60 | 100 | 80 | Earth continents+clouds, Jupiter bands+GRS, Saturn rings, ice giants, cratered, etc.
Sun rendering + glow layers | 8 | 16 | 12 | Additive blending sprites, pulse animation, opacity management
3D navigator (orbit camera + flyTo) | 24 | 40 | 32 | Smooth lerp, pitch/yaw, scroll zoom with log scaling, keyboard nav
Planet/moon/comet data entry | 16 | 24 | 20 | 34 bodies with orbital params, descriptions, classification, moon hierarchies
Particle belts (asteroid + Kuiper) | 8 | 12 | 10 | Randomized particle distributions, proper orbital zone ranges
Comet tails + extreme orbits | 12 | 20 | 16 | Tail sprites pointing away from Sun, near-parabolic orbit rendering, arc clamping
UI: info cards, HUD, minimap | 24 | 40 | 32 | Photo-viewer card, live orbital coords, zoom indicator, canvas minimap
Tour system (scripted flythrough) | 20 | 32 | 26 | Stop sequencing, narration, auto-advance, camera interpolation
Labels + hover tooltips | 8 | 12 | 10 | Canvas text sprites, distance-adaptive scaling, raycaster hover
Layer toggle system | 6 | 10 | 8 | Checkbox panel, visibility cascading through groups, keyboard shortcuts
Smart double-click (screen-space snap) | 8 | 16 | 12 | Project all bodies to screen coords, find nearest, handle edge cases
Habitable zone visualization | 4 | 6 | 5 | Annular ring at correct AU range, transparency, layer integration
Hill sphere visualization | 12 | 20 | 16 | Per-planet gravity zones, wireframe + fill, real-time position tracking
Actual Size toggle | 8 | 16 | 12 | Real AU radius math, render-loop override handling, educational UX
Help overlay + Log Truth overlay | 6 | 10 | 8 | Styled popups, keyboard wiring, educational copy
Arrow key cycling + nav buttons | 4 | 8 | 6 | Index tracking, flyTo integration, button wiring
Cross-browser testing + polish | 16 | 24 | 20 | WebGL compat, touch events, mobile, performance optimization
SOLAR SYSTEM SUBTOTAL | 296 | 486 | 391
MILKY WAY MAP |  |  |  | ~2,700 lines • Procedural galaxy with 80k+ particles
Galaxy structure (spiral arms algorithm) | 32 | 48 | 40 | Logarithmic spiral math, arm count/width/winding, per-particle color variance
Galactic core + bar + bulge | 16 | 24 | 20 | Core density distribution, bar geometry, dimming gradient
Background stars + disk fill particles | 12 | 20 | 16 | Random distributions, GlowTexture map, depth/transparency handling
Notable stars data (40+ entries) | 24 | 40 | 32 | Research, position estimation, descriptions, planet sub-entries, sky descriptions
Procedural star textures | 16 | 24 | 20 | Per-spectral-type rendering, glow layers, size categories
3D navigator (reused + extended) | 12 | 20 | 16 | Same orbit camera with galaxy-specific tuning, WASD nav (later removed)
Sector grid + coordinate grid | 12 | 20 | 16 | Named galactic sectors, lat/long lines, toggle system
Photo-viewer card + star info | 16 | 24 | 20 | Procedural star portrait, spectral class display, planet listings
Tour system (galaxy edition) | 16 | 24 | 20 | Different stops, narration, galaxy-scale camera movements
Mode switcher (All/Planets/Stars) | 8 | 12 | 10 | Filter logic, button UI, visibility cascading
Per-star distance scaling | 8 | 12 | 10 | Camera-distance-based sprite scaling to prevent jitter (tricky bug fix)
depthWrite / transparency fixes | 8 | 16 | 12 | Black box debugging, PointsMaterial configuration across 4 systems
Center dimming (radial fade) | 6 | 10 | 8 | Vertex color modulation, core opacity reduction, smooth gradient
Smart double-click + arrow cycling | 8 | 12 | 10 | Screen-space projection, selection tracking, UI buttons
Actual Size toggle | 6 | 10 | 8 | Scene traversal, PointsMaterial size override, sprite scaling
UI: layers, help, Log Truth, overlays | 10 | 16 | 13 | Panel system, hotkeys, educational content
Cross-browser testing + polish | 12 | 20 | 16 | Performance with 80k particles, WebGL limits, mobile
MILKY WAY SUBTOTAL | 222 | 352 | 287
GALAXY EXPLORER MAP |  |  |  | ~1,400 lines • Real astronomical data, 50+ galaxies
Galaxy data research + entry | 20 | 32 | 26 | RA/Dec/distance for 50+ galaxies, classifications, descriptions, image URLs
Sinh-compressed 3D positioning | 12 | 20 | 16 | Convert RA/Dec/distance to 3D scene coords with distance compression
Procedural galaxy textures | 16 | 24 | 20 | Per-morphology rendering (spiral, elliptical, irregular, lenticular)
RA/Dec grid + Mpc distance grid | 12 | 20 | 16 | Astronomical coordinate overlays, distance shells, labels
Info panel + galaxy images | 12 | 20 | 16 | Detail cards, Wikipedia image loading, pulsing detail indicators
Drunken tour (Elon's tour) | 8 | 12 | 10 | Randomized flythrough with comedic narration banners
Navigator + smart double-click | 10 | 16 | 13 | Orbit camera, plane intersection fallback, nearest-galaxy snap
Arrow cycling + nav buttons | 4 | 8 | 6 | Galaxy index tracking, flyTo, button wiring
Help overlay + Log Truth + Actual Size | 8 | 12 | 10 | Educational overlays, hotkeys, galaxy scaling toggle
Cross-browser testing + polish | 8 | 12 | 10 | Lighter map but still WebGL + sprite management
GALAXY EXPLORER SUBTOTAL | 110 | 176 | 143
CROSS-CUTTING WORK |  |  |  | Shared across all three maps
Architecture + project setup | 8 | 16 | 12 | File structure decisions, CDN management, shared patterns
Cross-map navigation links | 4 | 6 | 5 | Consistent link bar, styling, placement
Consistent UX patterns | 12 | 20 | 16 | Help button style, green glow animation, overlay patterns, hotkey conventions
Bug investigation + debugging | 24 | 40 | 32 | Black hole Sun, flyTo targeting (0,0,0), depth buffer issues, jitter, etc.
Iterative design feedback loops | 20 | 40 | 30 | Back-and-forth with stakeholder on dimming, zoom distances, label placement
Research + fact-checking | 16 | 24 | 20 | Orbital parameters, star positions, galaxy distances, educational accuracy
CROSS-CUTTING SUBTOTAL | 84 | 146 | 115
GRAND TOTAL (ALL THREE MAPS) | 712 | 1160 | 936
COST ESTIMATES
Solo senior dev ($125/hr) | 89000 | 145000 | 117000 | US market rate for senior Three.js/WebGL specialist
Small team (dev+designer+advisor) | 124600 | 203000 | 163800 | Blended rate including design & science review
Agency / contractor shop | 160200 | 261000 | 210600 | Typical agency rate with PM overhead
TIMELINE ESTIMATES
Solo dev (full-time) | 4.5 | 7.3 | 5.9 | Months at 160 hrs/month — no vacations, no context switching
Small team (2-3 people) | 2.2 | 3.6 | 2.9 | Months with parallelism but communication overhead
With LLM assistance (this project) | ~20 | hrs total |  | ~20 hours of conversation over a few sessions
Speedup factor: ~60-80× compared to traditional development. The iterative design loop (dimming, zoom tuning, bug hunting, educational features) accounts for most of the savings.